## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Conflict | When member pull code from github to their pc because they have same name variables and class | 1 |  |  | Khánh | 2023-05-02 | 13/02/2023 | iter2
cann't buid project | cấu hình sai file build.xml khi merge project về brand của mình | 2 |  |  | Khánh | 2023-09-02 | 14/02/2023 | iter2
This module has been not deployed | Project can't not deploy | 3 |  | done | Hoàng | 22/2/2023 | 23/2/2023 | iter2 |  | user profile
Conflict with main | add lib local | 4 |  | done | Hoàng | 24/2/2023 | 24/2/2023 | iter2 |  | Project
cann't login | Hasn't encode md5 into password | 5 |  | done | Kiên | 2023-03-03 | 2023-03-03 | iter3 |  | Login
Can't access to lesson after admin add/edit lession | Error: When admin added/edited lesson content, the system re-displayed the button "Đăng ký học phần" (Register for the course) while the expected result was the button "Cập nhật học phần(Update course)" and informed the user that the admin had changed the key learn ( After admin add/edit/delete lesionWhen you have not registered for the course, the system displays the button "Đăng ký học phần" (Register for the course) When you have registered for the course, the system displays the "Học phần đã được đăng ký" (Registered course) button. ) | 6 |  | done | Khang | 2023-05-03 | 2023-07-03 | iter3 |  | Add/Edit lession
Can't access to quiz management, game managerment, video management, content management | admin cant Can't access to quiz management, game managerment, video management, content management to edit for the same lesson after admin added/ edited content of lession 1 times | 7 |  | done | Khang | 2023-08-03 | 2023-10-03 | iter3 |  | Admin screen
System don’t give a message (change password) | When user change password,input filed is invalid, system don’t show message | 8 |  | done | Khang | 2023-11-03 | 14/03/2023 | iter3 |  | Change password
Can't send mail | When user send mail to verify account or upgrade to premium, System can't send a verify code to email user provided | 9 |  | done | Khang | 15/03/2023 | 15/03/2023 | iter3 |  | Verify account